Report on

“Tutorials”

For

Software Project Management - 4CS504ME25 B. Tech. Semester IV

Prepared By :

Gandhi Urva Yogeshkumar (23BCE078) Gajnotar Rakshit (23BCE077)

Institute of Technology,

Nirma University

Ahmedabad - 382481

October 2026

# Aim

To implement project monitoring and tracking tools including a Project Status Report, Earned Value Analysis (EVA), Milestone Tracking Chart and Defect Tracking Dashboard for the Hospital Management System (HMS) at a status date of Week 12.

# Objective

- Compare actual project performance against the 16-week baseline schedule (T5), effort estimates (T7) and defect baselines (T6).

- Establish a Red Amber Green (RAG) status threshold system for project health indicators.

- Perform Earned Value Analysis calculating PV, EV, AC, Schedule Variance, Cost Variance, SPI and CPI.

- Track deliverable milestones and measure schedule slip across Milestones M1 through M6.

- Build a Defect Tracking Dashboard analyzing closure rates, defect density, backlog trends and critical open bugs.

- Identify project deviations and formulate a fast-track recovery plan to protect the final Week 16 delivery date.

- Forecast final effort and cost at completion using EAC and ETC formulas.

# 1. Introduction

Planning a project is only the first step of project management. Once development starts, the manager must continuously check whether work is following the plan and take quick corrective action whenever things slip. This process is called project monitoring and tracking.

In this tutorial we monitor the Hospital Management System using our earlier baselines: the 16-week CPM schedule and milestones from T5, the 8.0 person-month effort estimate from T7, the defect and quality planning figures from T6 and the risk register from T9.

We review the project at a status date set at the end of Week 12 (conclusion of Sprint 5). At this point, five of the six core modules have been coded and integrated. We evaluate status using three monitoring tools: a Project Status Report with Earned Value Analysis, a Milestone Tracking Chart and a Defect Tracking Dashboard.

# 2. Monitoring and Tracking Framework

Our monitoring framework tracks five dimensions: Schedule, Effort and Cost, Milestone Completion, Defect Quality and Risks. Each metric is evaluated against fixed RAG thresholds agreed in advance:

| Status Indicator | Condition / Threshold | Action Required |
| --- | --- | --- |
| Green (On Track) | Deviation within +/- 5% of baseline plan (SPI >= 0.95, CPI >= 0.95) | Proceed according to regular sprint plan. |
| Amber (Caution) | Deviation between 5% and 10% behind plan (SPI 0.90 to 0.94, CPI 0.90 to 0.94) | Apply sprint recovery actions and use buffer. |
| Red (Critical) | Deviation > 10% behind plan (SPI < 0.90, CPI < 0.90, critical milestone slip) | Escalate to mentor and initiate replanning. |

# 3. Project Status Report (Status Date: End of Week 12)

At the end of Week 12, Sprint 5 (Billing and Invoice module) concluded. While Patient, Doctor, Appointment and Pharmacy modules are operational, testing the billing calculation engine and edge cases with prescription discounts caused minor delay.

## 3.1 Earned Value Analysis (EVA)

Earned Value Analysis connects schedule progress and effort in one integrated view:

| Metric Name | Abbreviation | Formula | Calculated Value | RAG Status |
| --- | --- | --- | --- | --- |
| Budget at Completion | BAC | Total Planned Project Budget | 8.00 Person-Months | Baseline |
| Planned Value | PV | Planned % * BAC (12 / 16 * 8.00) | 6.00 Person-Months | Baseline |
| Earned Value | EV | Completed Work % * BAC | 5.60 Person-Months | Amber |
| Actual Cost | AC | Actual Effort Expended to Date | 6.20 Person-Months | Amber |
| Schedule Variance | SV | EV - PV (5.60 - 6.00) | -0.40 Person-Months | Amber |
| Cost Variance | CV | EV - AC (5.60 - 6.20) | -0.60 Person-Months | Amber |
| Schedule Performance Index | SPI | EV / PV (5.60 / 6.00) | 0.933 (~0.93) | Amber |
| Cost Performance Index | CPI | EV / AC (5.60 / 6.20) | 0.903 (~0.90) | Amber |
| Estimate at Completion | EAC | BAC / CPI (8.00 / 0.903) | 8.86 Person-Months | Amber |
| Variance at Completion | VAC | BAC - EAC (8.00 - 8.86) | -0.86 Person-Months | Amber (10.7%) |
| Estimate to Complete | ETC | EAC - AC (8.86 - 6.20) | 2.66 Person-Months | Within Reserve |

## Analysis of EVA Results

- Schedule Performance: An SPI of 0.93 indicates the project is progressing at 93% of planned speed, representing roughly 0.40 person-months (about half a week) of schedule slip.

- Effort Efficiency: A CPI of 0.90 shows that for every person-month spent, 0.90 PM of planned work was earned. Additional time was spent resolving database locking in billing transactions.

- Forecast at Completion: EAC projects total effort at 8.86 PM. The forecast overrun of 0.86 PM (10.7%) is fully absorbed by the 10% to 15% contingency reserve established in T7, leaving the project financially viable.

# 4. Milestone Tracking Chart and Analysis

Tracking milestones against the baseline CPM schedule shows whether delivery delays propagate into downstream sprints:

| Milestone | Baseline Week | Actual / Forecast | Slip (Weeks) | Status |
| --- | --- | --- | --- | --- |
| M1: Inception and Architecture Frozen | Week 2 | Week 2 (Actual) | 0.0 | Achieved on time |
| M2: Patient and Doctor Operational | Week 6 | Week 6 (Actual) | 0.0 | Achieved on time |
| M3: Appointment Booking Live | Week 8 | Week 8 (Actual) | 0.0 | Achieved on time |
| M4: Pharmacy and Billing Verified | Week 12 | Week 12.5 (Actual) | +0.5 week | Achieved 0.5 wk late |
| M5: Dashboard and All Modules Coded | Week 14 | Week 14.5 (Forecast) | +0.5 week | At risk (Recoverable) |
| M6: Final Release and Submission | Week 16 | Week 16.0 (Forecast) | 0.0 | On track with recovery |

- Milestone Metrics: 4 of 4 milestones due by Week 12 have been achieved (100% completion rate), with 3 of 4 on time (75%).

- Critical Slip: The 0.5-week slip at M4 was caused by complex tax and discount logic in billing invoices. Because Billing sits on the critical path (T5), this delay pushed the forecast start of M5 back by half a week.

- Recovery Path: Because Sprint 7 contains integration and documentation buffers, fast-tracking integration during Sprint 6 allows M6 to finish exactly at Week 16.0 as planned.

# 5. Defect Tracking Dashboard

The Defect Tracking Dashboard summarizes testing progress, closure velocity and remaining open issues:

| Indicator | Value at Week 12 | Formula / Context |
| --- | --- | --- |
| Total Defects Logged | 32 Defects | Recorded since testing began in Sprint 1 (Week 3). |
| Total Defects Resolved | 26 Defects | Verified and closed in sprint bug fixes. |
| Currently Open Defects | 6 Defects | Active defects: 1 Critical, 2 High, 2 Medium and 1 Low. |
| Defect Closure Rate | 81.25% | Closed / Found = 26 / 32 * 100. |
| Net Backlog Change This Week | +1 Defect | 5 found and 4 closed during Sprint 5 review. |
| Defect Density So Far | 12.8 Defects / KLOC | 32 defects in approx 2.5 KLOC written to date. |
| Share of Expected Defects | 66.7% | 32 of 48 total errors anticipated before release (T6). |

## Important Open Defects (Critical and High)

The table below details all open defects requiring resolution prior to Sprint 6 admin module completion:

| ID | Module | Severity | Description | Age (Days) | Owner | Target |
| --- | --- | --- | --- | --- | --- | --- |
| D-019 | Billing | Critical | Invoice total does not recalculate when a medicine row is deleted | 3 | Urva | Week 13 (24h) |
| D-022 | Appointment | High | Allows booking appointment on a doctor's registered weekly day-off | 4 | Rakshit | Week 13 |
| D-024 | Pharmacy | High | Rapid concurrent checkout can decrement stock quantity below zero | 5 | Urva | Week 13 |
| D-027 | Patient | Medium | Phone number validation rejects valid 10-digit formats with spaces | 2 | Rakshit | Week 14 |
| D-029 | Doctor | Medium | Department filter dropdown does not reset after searching doctor name | 3 | Rakshit | Week 14 |
| D-031 | Billing | Low | Invoice print preview clips right margin border on smaller displays | 6 | Rakshit | Week 14 |

- Defect Density: 12.8 defects per KLOC written so far is consistent with our planned 14.55 errors per KLOC from T6.

- Backlog Trend: The open backlog of 6 defects is manageable. However, the 1 Critical (D-019) and 2 High defects (D-022 and D-024) must be closed within 48 hours to avoid blocking admin reporting.

# 6. Deviations Identified and Corrective Actions

Monitoring is useful only when it produces concrete corrective actions. The table below lists all deviations detected at Week 12 along with assigned owners and deadlines:

| # | Deviation Identified | Root Cause | Project Effect | Corrective Action Decided | Owner / Due |
| --- | --- | --- | --- | --- | --- |
| 1 | Billing testing slipped 0.5 week (SPI 0.93) | Complex pharmacy tax and discount rules in invoice calculation | Pushed Admin Dashboard start back by half a week | Fast-track: start admin frontend UI in parallel while finishing billing testing; freeze requirements | Urva / Wk 13 |
| 2 | Effort over plan by 0.60 PM (CPI 0.90) | Extra database locking and transaction debugging in billing | EAC rises to 8.86 PM, utilizing 10.7% reserve | Log effort daily; adopt strict unit test checklists before merging API changes to reduce rework | Both / Weekly |
| 3 | Critical defect D-019 open for 3 days | Event listener missed deletion event in React table state | Doctors and patients see incorrect billed amount | Fix invoice state recalculation within 24 hours; add automated Cypress test for deletion | Urva / Wk 13 |
| 4 | Concurrent appointment race risk (D-022 and R7) | Missing row lock on doctor slot during booking submit | Risk of double-booking same doctor time slot | Implement atomic PostgreSQL transaction with SELECT FOR UPDATE on doctor appointment slots | Urva / Wk 13 |
| 5 | Scope creep: requests for inpatient bed tracker | Clinical staff requested extra bed management screen | Threatens to derail Sprint 6 admin delivery | Enforce scope freeze; document bed tracker in future roadmap backlog for Version 2.0 | Rakshit / Wk 13 |
| 6 | DRE target of 90% requires protection | 32 of 48 expected errors found so far | Risk of defect leakage into hospital pilot trial | Dedicate full second week of Sprint 7 to joint regression testing across all 6 modules | Both / Wk 15 |

# 7. Forecast and Recovery Outlook

Based on our Week 12 tracking data, we compare the project outlook with and without the fast-track recovery plan:

| Scenario | Final Completion Date | Forecast Effort | Forecast Cost | Assessment |
| --- | --- | --- | --- | --- |
| Without Recovery Plan | Week 16.5 (+0.5 week late) | 8.86 PM | ₹1,99,350 | Late delivery; exceeds semester deadline. |
| With Fast-Track Recovery | Week 16.0 (On Schedule) | 8.86 PM | ₹1,99,350 | Delivers on time; fits inside 10% reserve. |

The recovery plan succeeds because the final sprint (Sprint 7) was designed with testing and documentation buffers. By resolving critical open defects within 48 hours and running integration checks concurrently with admin screens in Sprint 6, the project will finish on the baseline date of Week 16.0.

# 8. Conclusion

Monitoring the Hospital Management System at Week 12 with a status report, milestone tracking and defect dashboard provides clear visibility into project health. The Earned Value indicators (SPI 0.93 and CPI 0.90) show minor schedule slip and effort variance, caused by billing calculation complexities. Because these deviations were detected at Week 12, the team has time to execute the recovery plan, clear the 6 open defects and deliver the final release on schedule at Week 16.0 within our planned contingency reserve.